## INSTRUCTIONS
1 | Enter the Customer/Company Name (Cell C21, Hours Estimate Tab)
Enter the Workload (Cell C22, Hours Estimate Tab)
Enter Project Engineer(s) Name and Resource # (Cell C24, Hours Estimate Tab)
2 | Review and update the project tasks needed for the specific project/customer (Eng WBS Tab)
* If new tasks are needed, identify those tasks within the correct Phase and hours to complete it (WBS Tab)
* Make all necessary changes on the WBS tab. Those tasks will become part of the SOW. This step is VERY important to keep us on schedule during the project.
3 | Review the hours for the tasks on the Eng WBS Tab (the hours on the Project Hours Estimate Tab will automatically update)
* Do NOT make hours updates to the project summary box. ONLY update the hours within the WBS Tab
* These estimates should be an honest, realistic expectation on the amount of time each task will take. NOT best case.
* The project summary box on the Hours Estimate Tab pulls the total project hours from the scope section hours
4 | Review the amount of weeks each phase will take and update as needed in the "Weeks to complete Phase X" text box
* Do NOT enter any text/numbers into the Status Meetings duration box. This is automatically calculated based on the entry you make in the "Weeks to complete Phase X" to the right for each phase
* Please don't leave this blank. Status meetings occur every week.
5 | If you see any errors with the scope, tasks, or hours estimates please reach out to the PMO team so the template can be updated for future projects. The goal is to have accurate and helpful templates ready for all types of projects so the team only needs to make minor adjustments to account for the specifics of each project. If you have ideas to improve this template, reach out to the PMO team.

## Project Hrs Est
SKU: |  | 0 |  |  | Service Area within Scope
Estimated Partner Effort - Project Summary |  |  |  |  | Estimated partner effort - Mandatory Scope
|  |  |  | Delivery |  |  |  | Delivery
| Assess Environment |  |  | 3.75 |  | Phase 1 | Assess Environment | 3.25
| Design |  |  | 3 |  |  | Review SOW and Project Plan
| Deploy |  |  | 4 |  |  | Kick-off meeting with the Company
| Manage |  |  | 4
| Project Manager Time |  |  | 4.425
| Total Estimated partner effort |  |  | 19.175
[6 empty] | Phase 2 | Design | 2.5
Check INSTRUCTIONS Tab FIRST
| Weeks to complete Phase 1 |  | 1 | 0.5
| Weeks to complete Phase 2 |  | 1 | 0.5
| Weeks to complete Phase 3 |  | 1 | 0.5 |  | Phase 3 | Deploy | 3.5
| Weeks to complete Phase 4 |  | 1 | 0.5
| Total weeks |  | 4 | 2
| How many engineers are on this project? |  | 1 | 2
[6 empty] | Phase 4 | Manage | 3.5
Client:
Workload:
| Engineer(s): | Name & Resource #
[6 empty] | Estimated effort |  | 12.75

## PM Hours Estimate
|  | Duration |  |  | Task Description | PMO Steps
Phase 0 | Task | SKU- | Total PM Hrs for ###1: | 9.25 |  | Must be added to the Project Plan
0.01 | SOW review | 0.5 |  |  | Produce Existing/Source Tenant Configuration Document (Findings and Recommendations doc) | Dashboard or deck outlining Company's M365 configuration | Engineer submit to PM | PM check formatting and ECF letterhead | PM save in folder | PM send to Client with Deliverable acceptance paperwork | 5-day wait; address any issues
0.02 | Identify project prerequisites |  | 20% of Total Project Hours: | 2.95 | Identify and Document Target Tenant Design and Configuration (As Built Document draft) | Dashboard or deck outlining Company's M365 configuration | Engineer submit to PM | PM check formatting and ECF letterhead | PM save in folder | PM send to Client with Deliverable acceptance paperwork | 5-day wait; address any issues
0.03 | Create and send welcome letter | 0.25 | 30% of Total Project Hours: | 4.425 | Develop User Acceptance Test plan | This has to be approved by client and will cover EACH "source" type | Identify test cases from Client | Engineer submit to PM | PM check formatting and ECF letterhead | PM save in folder | PM send to Client with Deliverable acceptance paperwork
0.04 | Create project in BC | 0.5 |  |  | Review migration flow and communication plan | end user comms assistance by ECF team/PM
0.05 | Create Invoice | 0.25 |  |  | Identify user list for pilot and production batches | Obtain list of Pilot Users from Client | PM save list in Phase 1 folder
0.06 | Create/Update slides | 0.5 |  |  | Identify Secondary administrator (if required) | (needed for large migrations) | Client will need to identify
0.07 | Project management |  |  |  | Review migration flow and communication plan | end user comms assistance by ECF team/PM
| TOTAL | 2 |  |  | Document Target tenant settings and permissions | THIS NEEDS TO BE FIXED IN THE SOW TEMPLATE
|  |  | Traditionally ECF has added 30% of the engineer hours to cover the PM hours. We need to look at 20% minimum and start some truth data to go along with these numbers. |  | Project Closure Meeting | PM Schedule meeting for 5 days after completion of Phase 4
|  | Duration | If a project is >12hrs the PMO will automatically get 2 hours added to the SOW in order to create/invoice/deliverable paperwork
Phase 1 | Task | SKU- | Small projects only | Duration
0.08 | Initial comms with customer/team |  | SOW review | 0.5
0.09 | Project kickoff meeting | 0.75 | Identify project prerequisites | 0.25
0.05 | Create Invoice | 0.25 | Create project in BC | 0.5
0.11 | Draft/Send PM deliverable signature paperwork |  | Create Due Upon Signing invoice | 0.25
0.07 | Project management | 0.25 | Create deliverable invoice | 0.25
0.06 | status meetings prep (slides & burnchart) | 0.25 | Project closure in BC | 0.25
0.10 | Status meetings | 0.5 | TOTAL | 2
| TOTAL | 2
Duration
Phase 2 | Task | SKU-
0.05 | Create Invoice | 0.25
0.11 | Draft/Send PM deliverable signature paperwork
0.07 | Project management | 0.25
| status meetings prep (slides & burnchart) | 0.25
0.10 | Status meetings | 0.5
| TOTAL | 1.25
Duration
Phase 3 | Task | SKU-
0.05 | Create Invoice | 0.25
0.11 | Draft/Send PM deliverable signature paperwork
0.07 | Project management | 0.25
| status meetings prep (slides & burnchart) | 0.25
0.10 | Status meetings | 0.5
| TOTAL | 1.25
Duration
Phase 4 | Task | SKU-
0.05 | Create Invoice | 0.25
0.11 | Draft/Send PM deliverable signature paperwork
0.07 | Project management | 0.25
| status meetings prep (slides & burnchart) | 0.25
0.10 | Status meetings | 0.5
| TOTAL | 1.25
Duration
Project Close | Task | SKU-
0.05 | Create Invoice | 0.25
0.11 | Draft/Send PM deliverable signature paperwork
0.13 | Add all project paperwork as attachment in BC
0.14 | Close project in BC | 0.25
0.15 | Document lessons learned
0.07 | Project management | 0.25
| status meetings prep (slides & burnchart) | 0.25
0.10 | Closure meeting (status meeting) | 0.5
| TOTAL | 1.5
Note on D9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Project Management task covers any extras that aren't standard for all projects such as BC management, change requests, emails, track and manage risks/issues etc. Should we multiply this 1 hour duration by the number of weeks the Phase takes? For longer projects, there will be more PM things that come up.
Note on E11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Jennifer Smith @Brenner Schap Reply: Added a 20% and 30% reference point
Note on D19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Project Management task covers any extras that aren't standard for all projects such as BC management, change requests, emails, track and manage risks/issues etc. Should we multiply this 1 hour duration by the number of weeks the Phase takes? For longer projects, there will be more PM things that come up.
Note on D21: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Status meetings duration for PM is automatically calculated off the "Weeks to complete Phase #" entry that the engineer enters on their hours estimate tab.

## Eng WBS
SOW | BC Task | Est Hrs | Task Description | SOW | BC Task | Est Hrs | Task Description | SOW | BC Task | Est Hrs | Task Description | SOW | BC Task | Est Hrs | Task Description
X | X | 3.25 | Assess Environment (PHASE 1) | X | X | 2.5 | Design (PHASE 2) | X | X | 3.5 | Deploy (PHASE 3) | X | X | 3.5 | Manage (PHASE 4)
This section has mandatory tasks and will not be altered by an Engineer |  |  |  | This section has mandatory tasks and will not be altered by an Engineer |  |  |  | This section has mandatory tasks and will not be altered by an Engineer |  |  |  | This section has mandatory tasks and will not be altered by an Engineer
| X | 0.5 | Review SOW and Project Plan |  | X |  | Phase 2 Status Meetings |  | X |  | Phase 3 Status Meetings |  | X |  | Phase 4 Status Meetings
X | X | 0.75 | Kick-off meeting with the Company |  | X | 0.5 | Deliverable Paperwork (User Testing & UAT Doc) |  | X | 0.5 | Deliverable Paperwork (User Testing & UAT Doc) |  | X | 0.75 | Project Closure Meeting
| X |  | Phase 1 Status Meetings | The section below MUST be filled-out by the Engineer with each task |  |  |  | The section below MUST be filled-out by the Engineer with each task |  |  |  | The section below MUST be filled-out by the Engineer with each task
| X | 0.5 | Deliverable Paperwork (Findings and Recommendation Doc) | that is required to be completed in this phase. |  |  |  | that is required to be completed in this phase. |  |  |  | that is required to be completed in this phase.
The section below MUST be filled-out by the Engineer with each task |  |  |  | X | X | 1 | Identify each task that must be completed | X | X | 1 | Identify each task that must be completed | X | X | 0.75 | Identify each task that must be completed
that is required to be completed in this phase. | [6 empty] | In column H input only the number of hours needed for each task |  |  | 2 | In column M input only the number of hours needed for each task |  |  |  | In column R input only the number of hours needed for each task
X | X | 1 | Identify each task that must be completed |  |  | 1 | Columns F & G will be determined by the SDM |  |  |  | Columns K & L will be determined by the SDM |  |  | 2 | Columns P & Q will be determined by the SDM
|  | 0.5 | In column C input only the number of hours needed for each task
Columns A & B will be determined by the SDM